## Checklist Status
Finance Build Checklist Status
Status based on current implementation in repo and recent completion sweep.
Group | Task ID | Module | Task | Needs | Status | Short Description
Group 1 | 1.1 | M1 | Schema migration: add 5 columns to refunds table |  | Done | Refund workflow columns added and aligned with finance flow.
Group 1 | 1.2 | M1 | Create platform_settings table + seed refund threshold (200,000 paise) |  | Done | Platform settings table and refund threshold seed are implemented.
Group 1 | 1.3 | M10 | Create financial_audit_log table + REVOKE DELETE/UPDATE at DB level |  | Done | Implemented on shared audit_logs with append-only DB trigger and finance semantics.
Group 1 | 1.4 | M7 | Create legal_contacts table |  | Done | Legal contacts schema and history model are present.
Group 1 | 1.5 | M9 | Create module_access table |  | Done | Module access table exists and is used for finance gating.
Group 1 | 1.6 | M9 | Create pl_manual_entries table |  | Done | Manual P&L entries table exists with lock-compatible fields.
Group 1 | 1.7 | M5 | Create brand_tds_tracking table |  | Done | TDS tracking table and FY rollover flow are implemented.
Group 1 | 1.8 | M6 | Create user_consents table |  | Done | Consent storage schema is implemented.
Group 1 | 1.9 | M6 | Create data_deletion_requests table |  | Done | Deletion request schema and workflow fields are implemented.
Group 1 | 1.10 | M3 | Create commission_rules table + brand_payout_config table |  | Done | Commission rules and payout config foundations are implemented.
Group 1 | 1.11 | M2 | Create carrier_fee_schedule + cod_reconciliation + cod_reconciliation_runs tables |  | Done | COD reconciliation schema set is implemented.
Group 1 | 1.12 | M4 | Create hsn_master table |  | Done | HSN master schema exists and is wired into GST flow.
Group 2 | 2.1 | M1 | Admin UI: reason_code dropdown wired to reason_master + cost_allocation auto-suggest | 1.1, 1.3 | Done | Refund UI supports reason selection and cost allocation suggestions.
Group 2 | 2.2 | M1 | Approval gate logic: block processing above threshold, alert approver | 2.1 | Done | Threshold approval gate and awaiting-approval flow are implemented.
Group 2 | 2.3 | M1 | Razorpay refund hook: auto-write audit log on every state change | 1.3 | Done | Refund transitions and webhook outcomes now write finance audit entries.
Group 2 | 2.4 | M1 | Shiprocket reverse pickup auto-trigger for brand_fault / renivet_fault | 2.2 | Done | Reverse pickup creation is wired for the required fault categories.
Group 2 | 2.5 | M10 | Wire audit hooks: payout events, commission changes, bank detail changes | 1.3 | Done | Finance audit hooks cover payout, commission, and bank-detail events.
Group 2 | 2.6 | M10 | Wire audit hooks: GST exports, P&L edits, module access, data deletion | 1.3 | Done | Audit hooks cover GST export, P&L edits, module access, and deletion flows.
Group 2 | 2.7 | M7 | Admin UI: GRO edit form in Settings -> Legal Contacts (with audit log + alert) | 1.4, 2.5 | Done | GRO admin update flow is implemented with audit and alert behavior.
Group 2 | 2.8 | M7 | Website: Contact Us GRO section (dynamic from DB) | 1.4 | Done | Public GRO content is served from legal contact records.
Group 2 | 2.9 | M7 | Website: Footer Grievance Redressal link + ToS clause added | 2.8 | Done | Footer and ToS grievance additions were implemented.
Group 2 | 2.10 | M6 | Clerk signup: consent modal with required + optional consents | 1.8 | Partial | Consent storage is implemented, but end-to-end signup modal validation still needs final QA.
Group 2 | 2.11 | M6 | Account Settings: consent management page + Brevo/AiSensy propagation on opt-out | 2.10 | Partial | Consent management flow exists, but integration completeness should be verified in live testing.
Group 3 | 3.1 |  | Delhivery API: weekly COD fee schedule fetch + upsert to carrier_fee_schedule | 1.11 | Done | COD fee sync route and storage are implemented.
Group 3 | 3.2 |  | Delhivery API: daily remittance sync cron + auto-categorization logic | 3.1 | Done | Daily remittance sync and discrepancy categorization are implemented.
Group 3 | 3.3 |  | Shiprocket remittance sync | 1.11 | Partial | Primary COD implementation is live; Shiprocket remittance support should be treated as follow-up verification.
Group 3 | 3.4 |  | Admin dashboard: COD reconciliation table with status filters + one-click actions | 3.2, 3.3 | Done | COD dashboard workspace, filters, and actions are implemented.
Group 3 | 3.5 |  | Overdue/critical alert crons to AJ | 3.2 | Done | Alerting for COD failures and overdue states is wired.
Group 3 | 3.6 |  | Write-off flow: mandatory reason + proof upload + audit log | 3.4, 2.5 | Done | COD write-off requires proof and logs to finance audit.
Group 4 | 4.1 |  | Commission rule resolution engine (brand + category lookup, priority, fallback) | 1.10 | Done | Commission resolution engine is implemented.
Group 4 | 4.2 |  | Payout calculation engine (full formula per brand per cycle) | 4.1, 2.3 | Done | Cycle calculation supports commission, returns, holdback, overrides, and TDS.
Group 4 | 4.3 |  | Admin payout dashboard: per-brand review cards with expandable line items | 4.2 | Done | Payout review workspace is implemented.
Group 4 | 4.4 |  | Override flow: form + proof upload + dual-approval for overrides >Rs500 | 4.3, 2.5 | Done | Override flow supports proof and separate approver logic.
Group 4 | 4.5 |  | Payment execution: Razorpay Payout API for razorpay_route brands | 4.3 | Done | Automated payout execution path is implemented.
Group 4 | 4.6 |  | Payment execution: Manual NEFT txn ID capture flow for manual_neft brands | 4.3 | Done | Manual NEFT execution and confirmation flow is implemented.
Group 4 | 4.7 |  | Brand statement PDF generation (all sections including overrides, TDS) | 4.2 | Done | Statement PDF route exists and includes payout summary details.
Group 4 | 4.8 |  | Payout notifications: cycle day alert to AJ + execution confirmation to brand | 4.5, 4.6 | Done | Cycle alerts and payout event notifications are wired.
Group 4 | 4.9 |  | TDS deduction integrated into payout calculation + brand statement display | 4.2, 1.7 | Done | TDS is calculated during payout and surfaced in payout data.
Group 4 | 4.10 |  | Quarterly TDS summary export CSV for RegisterKaro | 4.9 | Done | Quarterly TDS export endpoint is implemented.
Group 5 | 5.0 |  | Prerequisite action (not IT): Confirm CSV format with RegisterKaro before any build starts | - | External | Business-side dependency; not a code deliverable.
Group 5 | 5.1 |  | Admin HSN import tool: CSV upload to populate hsn_master | 1.12 | Done | HSN admin import/manage flow is implemented.
Group 5 | 5.2 |  | Products table: add hsn_master FK, link existing HSN codes | 5.1 | Partial | HSN integration is implemented at report level; existing product linkage should be verified against production data.
Group 5 | 5.3 |  | GST rate auto-lookup + IGST/CGST/SGST split logic based on customer state | 5.2 | Done | GST split logic is implemented in report generation.
Group 5 | 5.4 |  | Pre-flight validation: flag missing HSN codes and brand GSTINs | 5.3 | Done | GST preview blocks export when required data is missing.
Group 5 | 5.5 |  | Combined GST + TCS CSV generator (two sections, one file) | 5.3, 5.4 | Done | Combined GST/TCS export generation is implemented.
Group 5 | 5.6 |  | Admin: Finance -> GST Report UI with preview summary and download | 5.5 | Done | GST workspace includes preview, validation, and export flows.
Group 6 | 6.1 |  | Account Settings: 'Delete My Account' flow with email verification | 1.9 | Partial | Deletion request and verification model exist; final account-settings UX should be validated end to end.
Group 6 | 6.2 |  | Admin: data deletion request review + execute panel | 1.9, 2.6 | Done | Admin review and execution flow is implemented.
Group 6 | 6.3 |  | Anonymization script: all 10 steps in atomic transaction | 6.2 | Done | Deletion executor and anonymization flow are implemented.
Group 6 | 6.4 |  | SLA cron: day 5 alert + day 7 escalation to AJ for pending requests | 1.9 | Done | Deletion SLA sweep cron is implemented.
Group 7 | 7.1 |  | Module access middleware check on monthly_pl API routes | 1.5 | Done | Monthly P&L APIs enforce explicit module access.
Group 7 | 7.2 |  | Admin Settings: Module Access management UI (super-admin only) | 1.5, 2.6 | Done | AJ-only grant/revoke UI is implemented.
Group 7 | 7.3 |  | Razorpay API: monthly gateway fee fetch | - | Partial | P&L currently derives gateway fees; direct monthly settlement import still needs hard validation.
Group 7 | 7.4 |  | Delhivery + Shiprocket API: monthly shipping invoice totals | 3.1, 3.3 | Partial | P&L shipping cost layer is present, but invoice-grade totals should be verified against carrier exports.
Group 7 | 7.5 |  | P&L data aggregation service (combines all auto sources) | 7.3, 7.4 | Partial | Aggregation service exists, but some auto-sources are still derived rather than provider-perfect.
Group 7 | 7.6 |  | P&L dashboard UI: auto fields with source badges + manual entry fields | 7.5, 1.6 | Done | Monthly P&L dashboard UI is implemented.
Group 7 | 7.7 |  | Lock month mechanism + pl_snapshots for historical preservation | 7.6, 2.6 | Done | Lock/unlock and snapshot preservation are implemented.
Group 7 | 7.8 |  | PDF export of locked P&L month | 7.7 | Done | Locked month PDF export route is implemented.
Group 8 | 8.1 |  | Audit log viewer UI with filters, diff viewer, CSV export | All hook tasks (2.5, 2.6, and later groups) | Done | Finance audit log viewer, filters, JSON diff view, and CSV export are implemented.
Group 8 | 8.2 |  | Attachment viewer: display proof docs from Uploadthing inline | 8.1 | Done | Audit viewer exposes attachment links for proof files.

## Summary
Completion Summary
Metric | Value
Total tasks | 60
Done | 51
Partial | 8
External | 1
Completion % (Done only) | 85%
Notes
Done = implemented in current repo state based on recent completion sweep.
Partial = code exists but still needs end-to-end verification or external-system hardening.
External = not an IT-owned deliverable.
Finance audit log is implemented via the shared audit_logs table, not a separate financial_audit_log table.