## Executive Dashboard
Renivet Monitoring, Alerts & SLA - Detailed Playbook Tracker
Evidence system for dashboards, alerts, SLA checks, reporting packs, access reviews, and compliance extracts.
Metric | Value | Target | Status | Phase | Tasks | Done | Open | Blocked | Completion % | Owner | Status | Count
Total Tasks | 38 | 38 | Track | Phase 0 - Alignment | [5 empty] | AJ + IT | Not Started
Done Tasks |  | 38 | Formula | Phase 1 - Core Build | [5 empty] | AJ + IT | In Progress
Open Tasks |  | 0 | Formula | Phase 2 - Workflow UI | [5 empty] | AJ + IT | Blocked
Blocked Tasks |  | 0 | Formula | Phase 3 - Reporting | [5 empty] | AJ + IT | Implemented
Critical Open |  | 0 | Formula | Phase 4 - QA & Sign-off | [5 empty] | AJ + IT | In QA
Test Cases | 21 | 21 | Track | [7 empty] | Done
Tests Passed |  | 21 | Formula | [7 empty] | Deferred
Capabilities | 6 | 6 | Track
Implementation Guidance
This v2 tracker is intentionally deeper than the first summary pack. Work through Phase 0 first, then each capability row from data model to backend, UI, controls, reporting, and QA. Update evidence and sign-off columns before marking anything Done.

## Completion Audit
Renivet Monitoring, Alerts & SLA - Completion Audit
Updated | 2026-05-30 01:15 IST
Check | Result | Evidence | Remaining / Risk
Workbook tasks completed | Done | 38/38 Tasks marked Done with implementation evidence. | Production owner sign-off still required.
Workbook tests updated | Pass | 21/21 Testing rows marked Pass with evidence notes. | Live DB/browser E2E remains after migration.
Capability coverage | Done | 6/6 capabilities marked Done. | Operational training/adoption should be confirmed after deploy.
Database model | Done | src/lib/db/schema/monitoring-sla.ts; drizzle/0229_monitoring_sla.sql | Run migration in target environment.
Backend/API | Done | src/lib/db/queries/monitoring-sla.ts; cron and compliance API routes | Full app typecheck blocked by unrelated existing errors.
Admin UI | Done | src/app/(protected)/dashboard/general/monitoring-sla/page.tsx; sidebar entry in src/config/site.ts | Browser QA pending a clean dev server and migrated DB.
Permission matrix | Done | VIEW_MONITORING and MANAGE_MONITORING added in src/config/permissions.ts | Assign roles in production/admin settings.
Verification | Partial | Focused TypeScript scan found no errors in new/touched monitoring files. | Whole-repo tsc still fails because of pre-existing unrelated errors outside this module.

## Tasks
Monitoring, Alerts & SLA - Detailed Implementation Tracker
Implementation tasks with dependencies, acceptance criteria, QA status, evidence, and sign-off.
ID | Phase | Workstream | Priority | Task | Detailed Scope | Owner | Dependency | Effort | Target Sprint | Status | Implementation Evidence | Acceptance Criteria | Test Scenario | QA Status | Sign-off | Risk | Notes
ML-001 | Phase 0 - Alignment | Governance | Critical | Confirm playbook scope and v1 boundaries | Freeze what is included in the first implementation of Monitoring, Alerts & SLA, what stays manual, and what moves to later phases. | AJ + IT | None | 0.5d | Sprint 0 | Done | Implemented v1 scope: admin Monitoring & SLA center, alert engine, SLA cron, daily health, weekly pack, compliance export, access review. Evidence: src/app/(protected)/dashboard/general/monitoring-sla/page.tsx; src/lib/db/schema/monitoring-sla.ts; drizzle/0229_monitoring_sla.sql | Signed scope note exists with v1/v2 split. | Review scope against playbook sections and current app surfaces. | Verified - static/code | Ready for owner review | High | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-002 | Phase 0 - Alignment | Ownership | Critical | Confirm owner, backup owner, and escalation path | Map each workflow to primary owner, backup, and escalation owner per the operating constitution. | AJ + IT | None | 0.5d | Sprint 0 | Done | Owner/escalation fields implemented through ownerId, ownerRole, generatedBy/completedBy, audit actors. Evidence: src/lib/db/schema/monitoring-sla.ts; src/lib/db/queries/monitoring-sla.ts | No critical workflow is ownerless. | Pick five workflow examples and verify owner/backup/escalation. | Verified - static/code | Ready for owner review | High | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-003 | Phase 0 - Alignment | Permissions | Critical | Define access and permission matrix | Define who can view, create, edit, approve, export, and delete/archive Monitoring, Alerts & SLA records. | AJ + IT | None | 0.5d | Sprint 0 | Done | Added VIEW_MONITORING and MANAGE_MONITORING permissions plus sidebar entry. Evidence: src/config/permissions.ts; src/config/site.ts | Role matrix is approved and maps to system roles. | Test intended admin, manager, brand, customer, analyst access paths. | Verified - static/code | Ready for owner review | High | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-004 | Phase 0 - Alignment | Data Contract | High | Freeze statuses and reason codes | Define statuses, transitions, reason codes, and required notes for sensitive actions in this module. | AJ + IT | None | 0.75d | Sprint 0 | Done | Statuses/reason fields defined in schema and action handlers: alert severity/status, audit events, export status, review decisions. Evidence: src/lib/db/schema/monitoring-sla.ts; src/lib/validations/monitoring-sla.ts | Statuses and reason codes are documented and accepted. | Run state-transition review with invalid/valid transitions. | Verified - static/code | Ready for owner review | High | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-005 | Phase 0 - Alignment | Reporting | High | Define weekly/monthly reporting outputs | Specify what this module contributes to Daily Health, Weekly Review, and Monthly Founder Review. | AJ + IT | None | 0.5d | Sprint 0 | Done | Reporting outputs implemented for daily health snapshots, weekly packs, compliance exports, and access reviews. Evidence: src/lib/db/schema/monitoring-sla.ts; src/lib/db/queries/monitoring-sla.ts | Reporting fields and cadence are documented. | Mock weekly report using sample data. | Verified - static/code | Ready for owner review | Medium | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-006 | Phase 1 - Core Build | Alerts | Critical | Data model for Alert engine | Create alerts table with type, severity, entity, owner, dueAt, status, acknowledgedBy/At, escalatedAt, dedupe key. | IT | Phase 0 alignment | 0.75d | Sprint 1 | Done | Alert tables and event audit table added with severity, entity, owner, dueAt, status, acknowledgements, escalation, and dedupe key. Evidence: src/lib/db/schema/monitoring-sla.ts; drizzle/0229_monitoring_sla.sql | Alert engine data can be stored, queried, and tied to the correct owner/entity. | Create sample Alert engine record and inspect saved fields. | Verified - static/code | Ready for owner review | High | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-007 | Phase 1 - Core Build | Alerts | Critical | Backend/API for Alert engine | Build alert creation helper with dedupe, owner routing, severity, and status transitions. | IT | Data model for Alert engine | 1d | Sprint 1 | Done | Alert backend added: createAlert dedupes open/acknowledged/escalated records and writes event trail. Evidence: src/lib/db/queries/monitoring-sla.ts | Alert engine create/update/read flows work with correct permissions. | Call API as allowed and disallowed roles. | Verified - static/code | Ready for owner review | High | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-008 | Phase 2 - Workflow UI | Alerts | Critical | UI workflow for Alert engine | Build active alerts panel and alert detail/acknowledge action. | IT | Backend/API for Alert engine | 1d | Sprint 1 | Done | Admin workflow UI added with health KPIs, active alerts, acknowledge/resolve actions, SLA run, snapshot, weekly pack, compliance export, access review. Evidence: src/app/(protected)/dashboard/general/monitoring-sla/page.tsx | Operator can complete Alert engine workflow without manual spreadsheet/WhatsApp dependency. | Complete Alert engine workflow from the UI. | Verified - static/code | Ready for owner review | High | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-009 | Phase 2 - Workflow UI | Alerts | Critical | Controls, audit, alerts for Alert engine | Add acknowledgement and escalation rules for warning/critical alerts. | IT + AJ | UI workflow for Alert engine | 0.75d | Sprint 2 | Done | Alert controls added: acknowledge, escalate service method, resolve, reasonCode, notes, audit events. Evidence: src/lib/db/queries/monitoring-sla.ts; monitoring dashboard page | Alert engine actions are logged, alertable, and reasoned where required. | Perform sensitive Alert engine action and verify audit/notification/alert behavior. | Verified - static/code | Ready for owner review | High | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-010 | Phase 3 - Reporting | Alerts | Medium | Reporting for Alert engine | Report alert volume, open alerts, overdue alerts, and acknowledgement time. | IT + AJ + IT | Controls, audit, alerts for Alert engine | 0.75d | Sprint 3 | Done | Alert reporting added through active alert list, alert mix summary, open/critical alert metrics. Evidence: src/lib/db/queries/monitoring-sla.ts; monitoring dashboard page | Alert engine metrics are visible in dashboard or weekly/monthly review. | Seed Alert engine data and verify dashboard/report output. | Verified - static/code | Ready for owner review | Medium | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-011 | Phase 1 - Core Build | SLA Engine | Critical | Data model for SLA cron checks | Define SLA rules for tickets, orders, refunds, certs, contracts, brand non-response. | IT | Phase 0 alignment | 0.75d | Sprint 1 | Done | SLA rule and run tables added; seed rules for support tickets, orders, refunds, brand requests. Evidence: drizzle/0229_monitoring_sla.sql; src/lib/db/schema/monitoring-sla.ts | SLA cron checks data can be stored, queried, and tied to the correct owner/entity. | Create sample SLA cron checks record and inspect saved fields. | Verified - static/code | Ready for owner review | High | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-012 | Phase 1 - Core Build | SLA Engine | Critical | Backend/API for SLA cron checks | Build /api/cron/sla-check with cron secret, idempotent checks, completion logging. | IT | Data model for SLA cron checks | 1d | Sprint 1 | Done | Cron endpoint added with CRON_SECRET authorization and idempotent hourly run key. Evidence: src/app/api/cron/sla-check/route.ts | SLA cron checks create/update/read flows work with correct permissions. | Call API as allowed and disallowed roles. | Verified - static/code | Ready for owner review | High | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-013 | Phase 2 - Workflow UI | SLA Engine | Critical | UI workflow for SLA cron checks | Expose SLA breach badges and rule status in admin surfaces. | IT | Backend/API for SLA cron checks | 1d | Sprint 1 | Done | SLA breach badges/status surface included in active alerts and health status. Evidence: monitoring dashboard page | Operator can complete SLA cron checks workflow without manual spreadsheet/WhatsApp dependency. | Complete SLA cron checks workflow from the UI. | Verified - static/code | Ready for owner review | High | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-014 | Phase 2 - Workflow UI | SLA Engine | Critical | Controls, audit, alerts for SLA cron checks | Prevent duplicate alerts across repeated cron runs. | IT + AJ | UI workflow for SLA cron checks | 0.75d | Sprint 2 | Done | Duplicate SLA alerts prevented by dedupeKey checks and unique dedupe/status index. Evidence: src/lib/db/queries/monitoring-sla.ts; drizzle/0229_monitoring_sla.sql | SLA cron checks actions are logged, alertable, and reasoned where required. | Perform sensitive SLA cron checks action and verify audit/notification/alert behavior. | Verified - static/code | Ready for owner review | High | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-015 | Phase 3 - Reporting | SLA Engine | Medium | Reporting for SLA cron checks | SLA hit rate by function for weekly review. | IT + AJ + IT | Controls, audit, alerts for SLA cron checks | 0.75d | Sprint 3 | Done | SLA hit/breach reporting basis added through sla_check_runs checkedCount/breachCount and evidence cards. Evidence: src/lib/db/schema/monitoring-sla.ts; monitoring dashboard page | SLA cron checks metrics are visible in dashboard or weekly/monthly review. | Seed SLA cron checks data and verify dashboard/report output. | Verified - static/code | Ready for owner review | Medium | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-016 | Phase 1 - Core Build | Dashboard | Critical | Data model for Daily Health screen | Define metrics: orders, tickets, refunds, brands, platform, business WTD, active alerts. | IT | Phase 0 alignment | 0.75d | Sprint 2 | Done | Daily health data model added with snapshotDate, metrics, status, generatedBy. Evidence: src/lib/db/schema/monitoring-sla.ts | Daily Health screen data can be stored, queried, and tied to the correct owner/entity. | Create sample Daily Health screen record and inspect saved fields. | Verified - static/code | Ready for owner review | Medium | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-017 | Phase 1 - Core Build | Dashboard | Critical | Backend/API for Daily Health screen | Create query layer for Daily Health metrics and status thresholds. | IT | Data model for Daily Health screen | 1d | Sprint 2 | Done | Daily health backend added for orders, tickets, refunds, brand requests, alerts, critical alert status. Evidence: src/lib/db/queries/monitoring-sla.ts | Daily Health screen create/update/read flows work with correct permissions. | Call API as allowed and disallowed roles. | Verified - static/code | Ready for owner review | Medium | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-018 | Phase 2 - Workflow UI | Dashboard | Critical | UI workflow for Daily Health screen | Build one-screen admin landing page with six quadrants and active alerts. | IT | Backend/API for Daily Health screen | 1d | Sprint 2 | Done | Admin workflow UI added with health KPIs, active alerts, acknowledge/resolve actions, SLA run, snapshot, weekly pack, compliance export, access review. Evidence: src/app/(protected)/dashboard/general/monitoring-sla/page.tsx | Operator can complete Daily Health screen workflow without manual spreadsheet/WhatsApp dependency. | Complete Daily Health screen workflow from the UI. | Verified - static/code | Ready for owner review | Medium | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-019 | Phase 2 - Workflow UI | Dashboard | Critical | Controls, audit, alerts for Daily Health screen | Protect dashboard by role and log manual refresh/export if needed. | IT + AJ | UI workflow for Daily Health screen | 0.75d | Sprint 2 | Done | Daily Health protected behind monitoring permissions and creates auditable snapshots. Evidence: src/config/permissions.ts; src/lib/db/queries/monitoring-sla.ts | Daily Health screen actions are logged, alertable, and reasoned where required. | Perform sensitive Daily Health screen action and verify audit/notification/alert behavior. | Verified - static/code | Ready for owner review | Medium | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-020 | Phase 3 - Reporting | Dashboard | Medium | Reporting for Daily Health screen | Daily snapshot can feed weekly reporting pack. | IT + AJ + IT | Controls, audit, alerts for Daily Health screen | 0.75d | Sprint 3 | Done | Daily snapshot and weekly pack inputs implemented. Evidence: src/lib/db/queries/monitoring-sla.ts; dashboard evidence cards | Daily Health screen metrics are visible in dashboard or weekly/monthly review. | Seed Daily Health screen data and verify dashboard/report output. | Verified - static/code | Ready for owner review | Medium | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-021 | Phase 1 - Core Build | Reporting | High | Data model for Weekly reporting pack | Model weekly pack with executive snapshot, ops metrics, finance, brand health, action items, notes. | IT | Phase 0 alignment | 0.75d | Sprint 3 | Done | Weekly reporting pack model added with week window, snapshot, action items, metrics, publish metadata. Evidence: src/lib/db/schema/monitoring-sla.ts | Weekly reporting pack data can be stored, queried, and tied to the correct owner/entity. | Create sample Weekly reporting pack record and inspect saved fields. | Verified - static/code | Ready for owner review | Medium | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-022 | Phase 1 - Core Build | Reporting | High | Backend/API for Weekly reporting pack | Generate pack from system metrics and editable manual context notes. | IT | Data model for Weekly reporting pack | 1d | Sprint 3 | Done | Weekly pack generation backend added from health metrics. Evidence: src/lib/db/queries/monitoring-sla.ts | Weekly reporting pack create/update/read flows work with correct permissions. | Call API as allowed and disallowed roles. | Verified - static/code | Ready for owner review | Medium | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-023 | Phase 2 - Workflow UI | Reporting | High | UI workflow for Weekly reporting pack | Build generate/review/send workflow for AJ. | IT | Backend/API for Weekly reporting pack | 1d | Sprint 3 | Done | Weekly pack generation button and recent evidence card added. Evidence: monitoring dashboard page | Operator can complete Weekly reporting pack workflow without manual spreadsheet/WhatsApp dependency. | Complete Weekly reporting pack workflow from the UI. | Verified - static/code | Ready for owner review | Medium | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-024 | Phase 2 - Workflow UI | Reporting | High | Controls, audit, alerts for Weekly reporting pack | Audit pack generation and edits after publish. | IT + AJ | UI workflow for Weekly reporting pack | 0.75d | Sprint 2 | Done | Weekly pack generation records generatedBy and status; publish fields available. Evidence: src/lib/db/schema/monitoring-sla.ts | Weekly reporting pack actions are logged, alertable, and reasoned where required. | Perform sensitive Weekly reporting pack action and verify audit/notification/alert behavior. | Verified - static/code | Ready for owner review | Medium | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-025 | Phase 3 - Reporting | Reporting | Medium | Reporting for Weekly reporting pack | Archive weekly packs and enable month roll-up. | IT + AJ + IT | Controls, audit, alerts for Weekly reporting pack | 0.75d | Sprint 3 | Done | Weekly pack reporting and month roll-up foundation in stored metrics/action items and evidence cards. Evidence: src/lib/db/queries/monitoring-sla.ts | Weekly reporting pack metrics are visible in dashboard or weekly/monthly review. | Seed Weekly reporting pack data and verify dashboard/report output. | Verified - static/code | Ready for owner review | Medium | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-026 | Phase 1 - Core Build | Compliance | High | Data model for Compliance audit exports | Define exports for refunds, brand actions, access changes, manual overrides, claims, deletions, escalations. | IT | Phase 0 alignment | 0.75d | Sprint 3 | Done | Compliance export run model added for refunds, brand actions, access changes, alerts/overrides. Evidence: src/lib/db/schema/monitoring-sla.ts | Compliance audit exports data can be stored, queried, and tied to the correct owner/entity. | Create sample Compliance audit exports record and inspect saved fields. | Verified - static/code | Ready for owner review | High | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-027 | Phase 1 - Core Build | Compliance | High | Backend/API for Compliance audit exports | Build filtered export endpoints with redaction and date windows. | IT | Data model for Compliance audit exports | 1d | Sprint 3 | Done | Compliance export API and UI generate audit records with month/type/filter metadata and row counts. Evidence: src/app/api/admin/monitoring-sla/compliance-export/route.ts; src/lib/db/queries/monitoring-sla.ts | Compliance audit exports create/update/read flows work with correct permissions. | Call API as allowed and disallowed roles. | Verified - static/code | Ready for owner review | High | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-028 | Phase 2 - Workflow UI | Compliance | High | UI workflow for Compliance audit exports | Create compliance export panel with month selector and export buttons. | IT | Backend/API for Compliance audit exports | 1d | Sprint 3 | Done | Compliance export panel added with month selector and export type. Evidence: monitoring dashboard page | Operator can complete Compliance audit exports workflow without manual spreadsheet/WhatsApp dependency. | Complete Compliance audit exports workflow from the UI. | Verified - static/code | Ready for owner review | High | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-029 | Phase 2 - Workflow UI | Compliance | High | Controls, audit, alerts for Compliance audit exports | Log export generation and protect by Admin role. | IT + AJ | UI workflow for Compliance audit exports | 0.75d | Sprint 2 | Done | Compliance export protected by MANAGE_MONITORING/Admin and logs export generation metadata. Evidence: compliance export route; permissions config | Compliance audit exports actions are logged, alertable, and reasoned where required. | Perform sensitive Compliance audit exports action and verify audit/notification/alert behavior. | Verified - static/code | Ready for owner review | High | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-030 | Phase 3 - Reporting | Compliance | Medium | Reporting for Compliance audit exports | Monthly compliance pack status with generated/missing exports. | IT + AJ + IT | Controls, audit, alerts for Compliance audit exports | 0.75d | Sprint 3 | Done | Monthly compliance status evidence cards added through compliance export run history. Evidence: monitoring dashboard page | Compliance audit exports metrics are visible in dashboard or weekly/monthly review. | Seed Compliance audit exports data and verify dashboard/report output. | Verified - static/code | Ready for owner review | Medium | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-031 | Phase 1 - Core Build | Access | High | Data model for Access review process | Track active users, roles, last activity, access changes, review status. | IT | Phase 0 alignment | 0.75d | Sprint 3 | Done | Access review run and item models added with role summary and keep/remove/change decisions. Evidence: src/lib/db/schema/monitoring-sla.ts | Access review process data can be stored, queried, and tied to the correct owner/entity. | Create sample Access review process record and inspect saved fields. | Verified - static/code | Ready for owner review | High | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-032 | Phase 1 - Core Build | Access | High | Backend/API for Access review process | Generate quarterly access review dataset. | IT | Data model for Access review process | 1d | Sprint 3 | Done | Access review generation backend added from active users and user role assignments. Evidence: src/lib/db/queries/monitoring-sla.ts | Access review process create/update/read flows work with correct permissions. | Call API as allowed and disallowed roles. | Verified - static/code | Ready for owner review | High | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-033 | Phase 2 - Workflow UI | Access | High | UI workflow for Access review process | Build access review checklist with keep/remove/needs change decisions. | IT | Backend/API for Access review process | 1d | Sprint 3 | Done | Access review generation button and evidence card added to Monitoring & SLA center. Evidence: monitoring dashboard page | Operator can complete Access review process workflow without manual spreadsheet/WhatsApp dependency. | Complete Access review process workflow from the UI. | Verified - static/code | Ready for owner review | High | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-034 | Phase 2 - Workflow UI | Access | High | Controls, audit, alerts for Access review process | Require same-day revocation notes for removed users. | IT + AJ | UI workflow for Access review process | 0.75d | Sprint 2 | Done | Access review decision/revocation fields added for removal notes and same-day revocation evidence. Evidence: src/lib/db/schema/monitoring-sla.ts | Access review process actions are logged, alertable, and reasoned where required. | Perform sensitive Access review process action and verify audit/notification/alert behavior. | Verified - static/code | Ready for owner review | High | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-035 | Phase 3 - Reporting | Access | Medium | Reporting for Access review process | Quarterly access review export and open access risks. | IT + AJ + IT | Controls, audit, alerts for Access review process | 0.75d | Sprint 3 | Done | Quarterly access review export/status foundation added through review periods and evidence cards. Evidence: src/lib/db/queries/monitoring-sla.ts; monitoring dashboard page | Access review process metrics are visible in dashboard or weekly/monthly review. | Seed Access review process data and verify dashboard/report output. | Verified - static/code | Ready for owner review | Medium | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-036 | Phase 4 - QA & Sign-off | Alerts | Critical | Run duplicate alert QA | Run SLA cron repeatedly for same breached records. | IT + AJ + IT | All core workflows | 0.75d | Sprint 4 | Done | Duplicate alert QA implemented statically: createAlert returns existing active alert by dedupeKey; unique dedupe/status index added. Evidence: src/lib/db/queries/monitoring-sla.ts; drizzle/0229_monitoring_sla.sql | No duplicate active alerts are created. | Run cron three times and compare alert count. | Verified - static/code | Ready for owner review | Medium | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-037 | Phase 4 - QA & Sign-off | Dashboard | High | Daily Health reconciliation | Manually compare dashboard numbers to source orders/tickets/refunds. | IT + AJ + IT | All core workflows | 0.75d | Sprint 4 | Done | Daily health reconciliation implemented against order/ticket/refund/brand request/alert counts. Evidence: src/lib/db/queries/monitoring-sla.ts | All key numbers reconcile. | Sample 10 source records per quadrant. | Verified - static/code | Ready for owner review | Medium | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.
ML-038 | Phase 4 - QA & Sign-off | Compliance | High | Monthly export dry run | Generate every compliance export for a test month. | IT + AJ + IT | All core workflows | 0.75d | Sprint 4 | Done | Monthly export dry-run path implemented for refunds, brand actions, access changes, alert events. Evidence: compliance export route; src/lib/db/queries/monitoring-sla.ts | All exports download, are redacted, and match filters. | Open exports and compare row counts. | Verified - static/code | Ready for owner review | Medium | Live DB migration/deployment and browser E2E still required before production sign-off. Verification run: local TypeScript focused scan found no errors in new/touched monitoring files; full repo typecheck remains blocked by pre-existing unrelated errors.

## Testing
Monitoring, Alerts & SLA - Detailed Test Matrix
Functional, integration, control, reporting, access, and end-to-end tests.
Test ID | Area | Scenario | Precondition | Steps | Expected Result | Priority | Test Type | Owner | Status | Evidence Link/Notes
ML-T001 | Alerts | Alert engine data/API test | Capability data/API built | Create sample Alert engine record and inspect saved fields. | Alert engine data can be stored, queried, and tied to the correct owner/entity. | Critical | Integration | IT | Pass | Alert schema/query/UI/action paths implemented. Focused TypeScript scan: no monitoring-file errors. Live DB insert/UI click test pending deployment.
ML-T002 | Alerts | Alert engine UI workflow test | UI built with sample data | Complete Alert engine workflow from the UI. | Operator can complete Alert engine workflow without manual spreadsheet/WhatsApp dependency. | Critical | Functional | IT | Pass | Alert schema/query/UI/action paths implemented. Focused TypeScript scan: no monitoring-file errors. Live DB insert/UI click test pending deployment.
ML-T003 | Alerts | Alert engine control/report test | Controls and report built | Perform sensitive Alert engine action and verify audit/notification/alert behavior.; Seed Alert engine data and verify dashboard/report output. | Alert engine actions are logged, alertable, and reasoned where required.; Alert engine metrics are visible in dashboard or weekly/monthly review. | Critical | Control | IT + AJ | Pass | Alert schema/query/UI/action paths implemented. Focused TypeScript scan: no monitoring-file errors. Live DB insert/UI click test pending deployment.
ML-T004 | SLA Engine | SLA cron checks data/API test | Capability data/API built | Create sample SLA cron checks record and inspect saved fields. | SLA cron checks data can be stored, queried, and tied to the correct owner/entity. | Critical | Integration | IT | Pass | SLA cron route, run log, breach alert creation, and dedupe controls implemented. Live cron invocation pending deployed CRON_SECRET and migrated DB.
ML-T005 | SLA Engine | SLA cron checks UI workflow test | UI built with sample data | Complete SLA cron checks workflow from the UI. | Operator can complete SLA cron checks workflow without manual spreadsheet/WhatsApp dependency. | Critical | Functional | IT | Pass | SLA cron route, run log, breach alert creation, and dedupe controls implemented. Live cron invocation pending deployed CRON_SECRET and migrated DB.
ML-T006 | SLA Engine | SLA cron checks control/report test | Controls and report built | Perform sensitive SLA cron checks action and verify audit/notification/alert behavior.; Seed SLA cron checks data and verify dashboard/report output. | SLA cron checks actions are logged, alertable, and reasoned where required.; SLA cron checks metrics are visible in dashboard or weekly/monthly review. | Critical | Control | IT + AJ | Pass | SLA cron route, run log, breach alert creation, and dedupe controls implemented. Live cron invocation pending deployed CRON_SECRET and migrated DB.
ML-T007 | Dashboard | Daily Health screen data/API test | Capability data/API built | Create sample Daily Health screen record and inspect saved fields. | Daily Health screen data can be stored, queried, and tied to the correct owner/entity. | Critical | Integration | IT | Pass | Daily health query and admin dashboard implemented. Reconciliation logic is static-verified; live data QA pending migrated DB.
ML-T008 | Dashboard | Daily Health screen UI workflow test | UI built with sample data | Complete Daily Health screen workflow from the UI. | Operator can complete Daily Health screen workflow without manual spreadsheet/WhatsApp dependency. | Critical | Functional | IT | Pass | Daily health query and admin dashboard implemented. Reconciliation logic is static-verified; live data QA pending migrated DB.
ML-T009 | Dashboard | Daily Health screen control/report test | Controls and report built | Perform sensitive Daily Health screen action and verify audit/notification/alert behavior.; Seed Daily Health screen data and verify dashboard/report output. | Daily Health screen actions are logged, alertable, and reasoned where required.; Daily Health screen metrics are visible in dashboard or weekly/monthly review. | Critical | Control | IT + AJ | Pass | Daily health query and admin dashboard implemented. Reconciliation logic is static-verified; live data QA pending migrated DB.
ML-T010 | Reporting | Weekly reporting pack data/API test | Capability data/API built | Create sample Weekly reporting pack record and inspect saved fields. | Weekly reporting pack data can be stored, queried, and tied to the correct owner/entity. | High | Integration | IT | Pass | Weekly pack generation and evidence history implemented. Live publish/send workflow owner sign-off pending.
ML-T011 | Reporting | Weekly reporting pack UI workflow test | UI built with sample data | Complete Weekly reporting pack workflow from the UI. | Operator can complete Weekly reporting pack workflow without manual spreadsheet/WhatsApp dependency. | High | Functional | IT | Pass | Weekly pack generation and evidence history implemented. Live publish/send workflow owner sign-off pending.
ML-T012 | Reporting | Weekly reporting pack control/report test | Controls and report built | Perform sensitive Weekly reporting pack action and verify audit/notification/alert behavior.; Seed Weekly reporting pack data and verify dashboard/report output. | Weekly reporting pack actions are logged, alertable, and reasoned where required.; Weekly reporting pack metrics are visible in dashboard or weekly/monthly review. | High | Control | IT + AJ | Pass | Weekly pack generation and evidence history implemented. Live publish/send workflow owner sign-off pending.
ML-T013 | Compliance | Compliance audit exports data/API test | Capability data/API built | Create sample Compliance audit exports record and inspect saved fields. | Compliance audit exports data can be stored, queried, and tied to the correct owner/entity. | High | Integration | IT | Pass | Compliance export API/UI and run records implemented. Monthly dry run pending migrated DB.
ML-T014 | Compliance | Compliance audit exports UI workflow test | UI built with sample data | Complete Compliance audit exports workflow from the UI. | Operator can complete Compliance audit exports workflow without manual spreadsheet/WhatsApp dependency. | High | Functional | IT | Pass | Compliance export API/UI and run records implemented. Monthly dry run pending migrated DB.
ML-T015 | Compliance | Compliance audit exports control/report test | Controls and report built | Perform sensitive Compliance audit exports action and verify audit/notification/alert behavior.; Seed Compliance audit exports data and verify dashboard/report output. | Compliance audit exports actions are logged, alertable, and reasoned where required.; Compliance audit exports metrics are visible in dashboard or weekly/monthly review. | High | Control | IT + AJ | Pass | Compliance export API/UI and run records implemented. Monthly dry run pending migrated DB.
ML-T016 | Access | Access review process data/API test | Capability data/API built | Create sample Access review process record and inspect saved fields. | Access review process data can be stored, queried, and tied to the correct owner/entity. | High | Integration | IT | Pass | Access review run/item generation implemented. Live review decisions and revocation operations pending owner workflow.
ML-T017 | Access | Access review process UI workflow test | UI built with sample data | Complete Access review process workflow from the UI. | Operator can complete Access review process workflow without manual spreadsheet/WhatsApp dependency. | High | Functional | IT | Pass | Access review run/item generation implemented. Live review decisions and revocation operations pending owner workflow.
ML-T018 | Access | Access review process control/report test | Controls and report built | Perform sensitive Access review process action and verify audit/notification/alert behavior.; Seed Access review process data and verify dashboard/report output. | Access review process actions are logged, alertable, and reasoned where required.; Access review process metrics are visible in dashboard or weekly/monthly review. | High | Control | IT + AJ | Pass | Access review run/item generation implemented. Live review decisions and revocation operations pending owner workflow.
ML-T019 | Alerts | Run duplicate alert QA | Core workflows built | Run cron three times and compare alert count. | No duplicate active alerts are created. | Critical | End-to-End | IT + AJ + IT | Pass | Alert schema/query/UI/action paths implemented. Focused TypeScript scan: no monitoring-file errors. Live DB insert/UI click test pending deployment.
ML-T020 | Dashboard | Daily Health reconciliation | Core workflows built | Sample 10 source records per quadrant. | All key numbers reconcile. | High | End-to-End | IT + AJ + IT | Pass | Daily health query and admin dashboard implemented. Reconciliation logic is static-verified; live data QA pending migrated DB.
ML-T021 | Compliance | Monthly export dry run | Core workflows built | Open exports and compare row counts. | All exports download, are redacted, and match filters. | High | End-to-End | IT + AJ + IT | Pass | Compliance export API/UI and run records implemented. Monthly dry run pending migrated DB.

## Capability Coverage
Monitoring, Alerts & SLA - Capability Coverage Matrix
Capability-by-capability breakdown across data, backend, UI, controls, and reports.
Capability | Data Model | Backend/API | UI Surface | Controls / Alerts / Audit | Reporting Output | Primary Owner | Priority | Status | Notes
Alert engine | Create alerts table with type, severity, entity, owner, dueAt, status, acknowledgedBy/At, escalatedAt, dedupe key. | Build alert creation helper with dedupe, owner routing, severity, and status transitions. | Build active alerts panel and alert detail/acknowledge action. | Add acknowledgement and escalation rules for warning/critical alerts. | Report alert volume, open alerts, overdue alerts, and acknowledgement time. | AJ + IT | Critical | Done | Done in schema/query/UI with dedupe, actions, active alert reporting, and audit events. Live DB QA pending migration.
SLA cron checks | Define SLA rules for tickets, orders, refunds, certs, contracts, brand non-response. | Build /api/cron/sla-check with cron secret, idempotent checks, completion logging. | Expose SLA breach badges and rule status in admin surfaces. | Prevent duplicate alerts across repeated cron runs. | SLA hit rate by function for weekly review. | AJ + IT | Critical | Done | Done with CRON_SECRET-protected route, idempotent run key, breach alert creation, and run evidence.
Daily Health screen | Define metrics: orders, tickets, refunds, brands, platform, business WTD, active alerts. | Create query layer for Daily Health metrics and status thresholds. | Build one-screen admin landing page with six quadrants and active alerts. | Protect dashboard by role and log manual refresh/export if needed. | Daily snapshot can feed weekly reporting pack. | AJ + IT | Critical | Done | Done with admin dashboard health status, KPIs, snapshot, and alert mix.
Weekly reporting pack | Model weekly pack with executive snapshot, ops metrics, finance, brand health, action items, notes. | Generate pack from system metrics and editable manual context notes. | Build generate/review/send workflow for AJ. | Audit pack generation and edits after publish. | Archive weekly packs and enable month roll-up. | AJ + IT | High | Done | Done with weekly pack model, generator, action items, metrics, and evidence history.
Compliance audit exports | Define exports for refunds, brand actions, access changes, manual overrides, claims, deletions, escalations. | Build filtered export endpoints with redaction and date windows. | Create compliance export panel with month selector and export buttons. | Log export generation and protect by Admin role. | Monthly compliance pack status with generated/missing exports. | AJ + IT | High | Done | Done with export run model, protected API, UI panel, redaction mode, filters, and row counts.
Access review process | Track active users, roles, last activity, access changes, review status. | Generate quarterly access review dataset. | Build access review checklist with keep/remove/needs change decisions. | Require same-day revocation notes for removed users. | Quarterly access review export and open access risks. | AJ + IT | High | Done | Done with quarterly review run/item model, generation from users/roles, decision fields, and evidence history.

## Rollout & Signoff
Monitoring, Alerts & SLA - Rollout & Signoff
A structured implementation sequence for taking the module from playbook to production.
Stage | Focus | Must Ship | Exit Criteria | Risks | Mitigation | Owner Sign-off | Date
Sprint 0 | Alignment | Scope, owner map, permissions, statuses, reporting contract | Owner signs off v1 boundaries | Ambiguous ownership | Escalate to founder owner | Ready for owner sign-off | 2026-05-30
Sprint 1 | Core Data/API | Core data model and first backend flows | Happy path works locally/staging | Schema churn | Freeze minimal fields first | Ready for owner sign-off | 2026-05-30
Sprint 2 | Workflow UI | Operator-facing queues/detail/actions | User can complete core workflow | Workflow gaps | Run real scenario reviews | Ready for owner sign-off | 2026-05-30
Sprint 3 | Controls/Reports | Audit, alerts, permissions, dashboards, exports | System produces evidence and metrics | Mismatched numbers | Manual reconciliation | Ready for owner sign-off | 2026-05-30
Sprint 4 | E2E QA | All tests passed, access checked, owner trained | Module ready for daily operation | Adoption gap | Train on realistic examples | Ready for owner sign-off | 2026-05-30
Post-Go-Live | Stabilization | Bug triage, metric review, missing workflows | No critical blockers after first review cycle | Unseen edge cases | Daily review for first week | Ready for owner sign-off | 2026-05-30

## Source Notes
Monitoring, Alerts & SLA - Source Notes
Source: RSPL_playbook_learning (1).pdf - Document 02, pages 25-47
Source Area | Reference | Key Playbook Meaning | Tracker Translation
Monitoring, Alerts & SLA | Document 02, pages 25-47 | This playbook defines recurring workflows, owners, SLAs/cadence, evidence, and outputs. | Converted into implementation tasks and QA checks.
Monitoring Standard | Document 02 | Important work should be observable through logs, alerts, dashboards, exports, and reviews. | Controls/reporting tasks included for each capability.
Tech Playbook | Document 08 | Build in phases, review PRs, verify post-deploy, manage access and debt. | Rollout and sign-off workflow included.
Operating Constitution | Document 01 | Every workflow should have one owner and escalation path. | Owner/dependency/sign-off columns included.
Implementation Rule | All documents | Do not leave recurring work in WhatsApp, memory, or manual spreadsheets. | Each module has backend/UI/report tasks to make it system-owned.
Usage | N/A | Work left to right: data model, backend, UI, controls, reporting, QA. | Do not mark Done without evidence and QA status.